## Slide 1
Roxburgh Entertainment Centre
Central Otago District Council

## Slide 2: Hall, Theatre and Cinema
The Roxburgh Hall begun construction in 1875.
Beginnings

## Slide 3: Hall, Theatre and Cinema
In 1918 the Hall was vested to the Borough Council
In 1926 the Borough Council invested in a projection machine.
Hall moved and the new building was reported open in the Otago Witness in March 1931.
Renovations were undertaken over the decades to become the Roxburgh Entertainment Centre.
Beginnings

## Slide 4: Fire Disaster
Thursday 6th February 2025

## Slide 5
Post fire destruction, façade investigated.
Fire aftermath

## Slide 6
Façade removal
Site cleared and free of asbestos
Site clearance, metal removal

## Slide 7: Immediate Considerations
Asbestos: no complications additional testing and removal, clearance cert has been issued.
Historical ramifications: Because the site is pre 1900’s it is deemed a historical site and all care needs to be taken. Engaged Origin Consultants who have experience in this area and are liaising with Heritage NZ for an archaeological authority to continue site works.
Dust mitigations: Lake Roxburgh Contracting are investigating options:
  K-line with timer estimated cost $2750
  Gravel (potential re-use in car park or similar)

## Slide 8: Remediation Costs
Costs incurred to date
Supplier | Description | Estimate | Value
Fulton Hogan | Traffic Management 14-16 Feb | $2,000.00 | $1,811.75
 | Traffic Management 25 Feb | $2,000.00 | $1,952.00
 | Traffic Management Plan, 17 - 22 Feb | $3,000.00 | $2,994.50
WSP | Engineers | $20,000.00 | $21,412.50
Scope | Asbestos plans, testing and rates | $30,000.00 | $17,155.70
Cougar | Security check 3 x daily | $10,500.00 | $2,400.00
Shannon's HVAC | Fire agent - official call out | $150.00 | 
Origin | Memo Report | $3,000.00 | $2,190.00
 | Archaeological Authority | $3,000.00 | 
 | Site visit - soak pit | $1,500.00 | 
Consultex | Asbestos removal and site clearance | $10,000.00 | $4,137.50
Scope Resources | Victoria Flats Landfill | $50,000.00 | $17,238.00
Lake Roxburgh Contracting | Demolition, removal works | $300,000.00 | $149,822.00
TOTALS |  | $435,150.00 | $221,113.95

## Slide 9: Insurance Overview
We have a total sum insured of c.$6.4m
The total sum insured includes everything required to replace the building
However, a clause in the policy requires the building to be replaced ‘like for like’
As such, a Quantity Survey is being completed by Halliwell QS to confirm the cost to reinstate the building in a ‘like for like’ way
If this QS exceeds or meets the total sum insured ($6.3m), we will be able to utilise the full amount
If this QS is returned with a lower value than $6.3m, we will engage our own QS to get a second opinion and enter negotiations with the insurer. This will be supported by our broker, AON.
What is our cover and where are we now?

## Slide 10: Insurance Overview
Once a figure is decided upon, the insurer can decide to pay out the full amount in one lump sum, or work on a payment per invoice basis
Given the size of this claim, this will be dependent on their calculations as to whether there is more cost involved in drawing down funds for a one-off lump sum, or managing the admin of the claim for the next 18-24 months
We have already paid out for demolition and site clean up and we are likely to be able to obtain a progress payment for costs already incurred in the near future
We are working through this process with AON and an insurer-appointed loss adjustor from McLaren’s, based in Alexandra
How does this all work?

## Slide 11: Procurement Options
Our aim is to rebuild the Roxburgh Hall and Entertainment Centre in a timely manner, to provide a much-needed community space, theatre, and cinema, within the available budget
In order to get the most from our procurement process, we intend to complete market engagement
  Market engagement is the process of communicating with potential suppliers to understand their interest in the project, their thoughts on what successful or effective procurement would look like from a supplier point of view, and how we can achieve the best outcome for our community
  For this procurement, we would complete this in the form of interviews with potential suppliers, each lasting around 30 minutes. As such, the process itself wouldn’t take long and would be completed at the very start of the procurement process, so any insights can be taken on board when in the planning phase of procurement
Procurement Overview

## Slide 12: Procurement Options
Traditional Two-Stage Process: Registration of Interest (ROI), followed by Request for Proposal (RFP)
This would be a joint bid from Architects and Construction Firms
  Council would shortlist 3 tenderers from the ROI and request a fully costed design from each
  We would give consideration to paying a sum for all designs so that elements from unsuccessful designs can be included in final design
    Only 3 total RFP responses for Manuherikia Hub, but an ROI process is still required to ensure no more than 3 RFP responses are received in total
    Target-price tenders required to ensure cost is within budget
    If no consideration given to paying for designs, interest may not be high (costs to produce and QS a design to be submitted as part of a tender are very high)
Option 1

## Slide 13
One Stage Quality-Based RFP – Joint Bid
  Design and build RFP from joint architect and construction bid to be assessed on quality attributes only, without price
  Winning tenderer will need to become Council’s partner in designing and building new hall to budget
  This will be a fully collaborative approach to designing and building the new hall, with input from Council in the design as it progresses
Option 2a

## Slide 14: Procurement Options
One Stage Quality-Based RFP – Design Only
  Design RFP to be assessed on quality attributes only, without price
  Winning tenderer will need to become Council’s partner in designing the new hall to budget
  A separate RFP will be undertaken for the construction based up our agreed design
Option 2b RFP for design only

## Slide 15: Procurement Options
Lean Agile Procurement – Joint Bid
  Market engagement required with contractors to understand if they would be interested in participating in this approach
  ROI completed as first stage to shortlist no more than 4 tenderers
  A brief is documented and sent out as a Request to Participate
  In a workshop with all suppliers, or individually, each supplier provides ideas and thoughts to achieve the desired outcomes, identifying key constraints, capabilities, and ability to align with CODC
  At the end of the workshop/s, an evaluation team will rate each supplier and decide upon a partner to complete the design and build
    Benefits: faster process than traditional procurement, potentially more interest in market as full design not required as part of bid, leads to partnership approach
    Drawbacks: untested at CODC, interest from suppliers may be limited
Option 3

## Slide 16: Procurement Option
Design and build will require partnerships to be formed by contractors and architects to form a bid
Budget will be made clear to all potential suppliers
Suggest completing market engagement prior to deciding on any approach
Feedback from previous construction procurements:
  Designs being developed without contractor input can lead to costly variations
  Architects like to have client’s opinions when designing – designing to RFP spec can often lead to concessions being made without agreement
  Costly to fully design and QS for target price which can lead to lack of interest in the market if no incentive is included in the traditional approach
General Considerations

## Slide 17: Cromwell Memorial Hall
Cinema Ideas

## Slide 18: Recent Hall build
Luggate Memorial Centre – first passive community building in the Southern Hemisphere
Approx build price $5,000,000

## Slide 19: Manuherikia Community Hub
Indicative only